## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Sanjay Krishnan K | 14-02-2026 | Missing values in dataset | Sprint 1 | Sanjay Krishnan K | Data Issue | Cleaned dataset and handled null values | 16-02-2026 | Closed | Resolved
2 | Sanjay Krishnan K | 15-02-2026 | Incorrect user-item mapping | Sprint 1 | Sanjay Krishnan K | Functional Issue | Fixed pivot logic | 16-02-2026 | Closed | Working correctly
3 | Sanjay Krishnan K | 01-03-2026 | Low model accuracy | Sprint 2 | Sanjay Krishnan K | Model Issue | Implemented hybrid model | 02-03-2026 | Closed | Improved accuracy
4 | Sanjay Krishnan K | 02-03-2026 | Cold start problem | Sprint 2 | Sanjay Krishnan K | Model Issue | Added rating-based system | 03-03-2026 | Closed | Handled
5 | Sanjay Krishnan K | 14-03-2026 | Incorrect evaluation metrics | Sprint 3 | Sanjay Krishnan K | Testing Issue | Validated MAE and RMSE | 16-03-2026 | Closed | Corrected
6 | Sanjay Krishnan K | 15-03-2026 | Slow recommendation response | Sprint 3 | Sanjay Krishnan K | Performance Issue | Optimized computations | 16-03-2026 | Closed | Improved
7 | Sanjay Krishnan K | 28-03-2026 | Integration issues | Sprint 4 | Sanjay Krishnan K | Integration Issue | Fixed backend-frontend integration | 30-03-2026 | Closed | Resolved
8 | Sanjay Krishnan K | 29-03-2026 | Deployment instability | Sprint 4 | Sanjay Krishnan K | System Issue | Improved testing and stability | 30-03-2026 | Closed | Stable

## Sheet2
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | [Your Name] | 2025-12-05 | Missing values in user purchase history causing errors in user-item matrix | Milestone 1 (Weeks 1–2) | Self | Logical | Cleaned dataset and filled missing values | 2025-12-05 | Closed | User-item matrix ready for model training
2 | [Your Name] | 2025-12-16 | Recommendation model gives irrelevant suggestions for new users | Milestone 2 (Weeks 3–4) | Self | Logical | Added fallback logic for cold-start users | 2025-12-16 | Closed | Recommendations now relevant for new users
3 | [Your Name] | 2025-12-29 | Duplicate products appear in recommendation output | Milestone 3 (Weeks 5–6) | Self | Maintainability | Implemented duplicate filtering in output | 2025-12-29 | Closed | Recommendations are now unique
4 | [Your Name] | 2026-01-05 | Recommendation response time is slow on product page | Milestone 3 (Weeks 5–6) | Self | Standards | Optimized query and caching logic | 2026-01-05 | Closed | Response time reduced to <2 seconds
5 | [Your Name] | 2026-01-12 | Frontend integration shows errors while rendering suggestions | Milestone 4 (Weeks 7–8) | Self | Logical | Adjusted API response format and frontend code | 2026-01-12 | Closed | Recommendations display correctly